## Project Status Dashboard
Project Status Dashboard
Executive project status with RAG indicators across all workstreams
Workstream | Lead | % Complete | RAG | Key Achievement | Next Milestone | Issue | Risk
Overall Project | PM | 55% | 🟢 | Execution phase on track | UAT sign-off by 15-Jun | None | Resource risk monitored
Design | Design Lead | 100% | 🟢 | All designs approved by client | — | None | None
Development | Dev Lead | 70% | 🟡 | Core modules complete | Module 4 by 20-May | API delay | Integration complexity
Testing & QA | QA Lead | 30% | 🟡 | Test cases written (80%) | Test execution from 25-May | Test env delay | Insufficient test data
Infrastructure | IT Lead | 80% | 🟢 | Cloud setup complete | Security audit 01-Jun | None | Cost overrun risk
Change Management | HR Lead | 40% | 🟡 | Stakeholder mapping done | Training plan by 15-May | Low adoption risk | Change resistance
Finance / Budget | Finance | 55% | 🟢 | Mid-point budget review done | Month 4 actuals review | None | 5% over on IT costs
Legal / Compliance | Legal | 90% | 🟢 | Contracts signed | Final compliance check Jun | None | Regulatory update watch

## 📌 More Info
Excel Gurukul Online — Project Management › Execution Phase
Need More Templates? | Browse 500+ free & premium Excel templates | https://excelgurukulonline.com/
Browse All Categories | 20 categories — find the right template for you | https://excelgurukulonline.com/templates.php
More Project Management Templates | See all Project Management templates | https://excelgurukulonline.com/templates.php?cat=project-management
More Execution Phase Templates | See all Execution Phase templates | https://excelgurukulonline.com/templates.php
Request Custom Template | Need something specific? We can help! | info@excelgurukulonline.com
💡 All templates on Excel Gurukul Online are free to download. Premium versions with advanced features available at nominal INR pricing. Visit https://excelgurukulonline.com to explore all Project Management templates.
© 2026 Excel Gurukul Online ¦ https://excelgurukulonline.com ¦ info@excelgurukulonline.com