## Kanban Board (Agile)
Kanban Board (Agile)
Visual task management board — Backlog, In Progress, Review, Done
Task ID | Task Description | Assigned To | Priority | Story Points | Backlog | In Progress | Review | Done | Sprint
T-001 | Design homepage wireframes | UX Designer | High | 3 |  |  | ✓ | Done | Sprint 1
T-002 | Set up development environment | Dev Lead | High | 2 |  |  |  | Done | Sprint 1
T-003 | Build user authentication module | Dev A | Critical | 5 |  | ✓ Active |  |  | Sprint 2
T-004 | Create API endpoints (CRUD) | Dev B | High | 8 |  | ✓ Active |  |  | Sprint 2
T-005 | Database schema design | Dev Lead | High | 3 |  |  | ✓ | Done | Sprint 1
T-006 | Payment gateway integration | Dev A | Critical | 13 | Backlog |  |  |  | Sprint 3
T-007 | Email notification service | Dev B | Medium | 5 | Backlog |  |  |  | Sprint 3
T-008 | Write unit tests — Auth module | QA | High | 3 |  | ✓ Active |  |  | Sprint 2
T-009 | Performance testing | QA | Medium | 5 | Backlog |  |  |  | Sprint 4
T-010 | User acceptance testing | QA | High | 8 | Backlog |  |  |  | Sprint 4
T-011 | Deployment to staging | Dev Lead | High | 3 | Backlog |  |  |  | Sprint 3
T-012 | Production go-live | PM | Critical | 5 | Backlog |  |  |  | Sprint 5

## 📌 More Info
Excel Gurukul Online — Project Management › Execution Phase
Need More Templates? | Browse 500+ free & premium Excel templates | https://excelgurukulonline.com/
Browse All Categories | 20 categories — find the right template for you | https://excelgurukulonline.com/templates.php
More Project Management Templates | See all Project Management templates | https://excelgurukulonline.com/templates.php?cat=project-management
More Execution Phase Templates | See all Execution Phase templates | https://excelgurukulonline.com/templates.php
Request Custom Template | Need something specific? We can help! | info@excelgurukulonline.com
💡 All templates on Excel Gurukul Online are free to download. Premium versions with advanced features available at nominal INR pricing. Visit https://excelgurukulonline.com to explore all Project Management templates.
© 2026 Excel Gurukul Online ¦ https://excelgurukulonline.com ¦ info@excelgurukulonline.com