## Planned vs Actual Tracker
Planned vs Actual Tracker
Compare planned vs actual progress on schedule, budget and scope
Milestone / Activity | Planned Start | Planned End | Actual Start | Actual End | Planned Cost (₹) | Actual Cost (₹) | Variance (₹) | % Complete | Status | Remarks
Project Kickoff | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 0 | 0 | 0 | 100% | Done | On schedule
Requirements Gathering | 2026-01-02 | 2026-01-15 | 2026-01-02 | 2026-01-16 | 2,00,000 | 1,90,000 | 10,000 | 100% | Done | 1 day late, under budget
Design Phase | 2026-01-16 | 2026-02-05 | 2026-01-17 | 2026-02-07 | 4,00,000 | 3,80,000 | 20,000 | 100% | Done | 2 days late, under budget
Development — Sprint 1 | 2026-02-08 | 2026-02-21 | 2026-02-08 | 2026-02-21 | 6,00,000 | 6,20,000 | -20,000 | 100% | Done | On time, over budget
Development — Sprint 2 | 2026-02-22 | 2026-03-07 | 2026-02-22 | 2026-03-10 | 6,00,000 | 6,50,000 | -50,000 | 100% | Done | 3 days late
Development — Sprint 3 | 2026-03-08 | 2026-03-21 | 2026-03-08 | — | 6,00,000 | 4,00,000 | — | 67% | Active | In progress
Testing Phase | 2026-03-22 | 2026-04-04 | — | — | 3,00,000 | 0 | — | 0% | Pending | Not started
UAT | 2026-04-05 | 2026-04-11 | — | — | 1,00,000 | 0 | — | 0% | Pending | Awaiting dev completion
Deployment | 2026-04-12 | 2026-04-14 | — | — | 50,000 | 0 | — | 0% | Pending
Project Closure | 2026-04-15 | 2026-04-20 | — | — | 50,000 | 0 | — | 0% | Pending
TOTAL |  |  |  |  | 28,50,000 | 22,40,000 | — | 71%

## 📌 More Info
Excel Gurukul Online — Project Management › Execution Phase
Need More Templates? | Browse 500+ free & premium Excel templates | https://excelgurukulonline.com/
Browse All Categories | 20 categories — find the right template for you | https://excelgurukulonline.com/templates.php
More Project Management Templates | See all Project Management templates | https://excelgurukulonline.com/templates.php?cat=project-management
More Execution Phase Templates | See all Execution Phase templates | https://excelgurukulonline.com/templates.php
Request Custom Template | Need something specific? We can help! | info@excelgurukulonline.com
💡 All templates on Excel Gurukul Online are free to download. Premium versions with advanced features available at nominal INR pricing. Visit https://excelgurukulonline.com to explore all Project Management templates.
© 2026 Excel Gurukul Online ¦ https://excelgurukulonline.com ¦ info@excelgurukulonline.com