## Weekly Status Report
Weekly Status Report
Project health dashboard with RAG status and key metrics
Section | Details | RAG | Comments
Project Name | [Project Name] |  | Week ending: [Date]
Overall Status | On Track | 🟢 | All major milestones met
Schedule | On Track | 🟢 | Week 8 of 22 — as planned
Budget | At Risk | 🟡 | Variance of 8% — monitoring
Scope | On Track | 🟢 | No scope changes this week
Resources | On Track | 🟢 | All resources available
Risks | At Risk | 🟡 | 2 new risks identified
Issues | On Track | 🟢 | 1 issue resolved this week
Milestones This Week | Design phase completed | 🟢 | Delivered on time
Next Week Plans | Begin development sprint | 🟢 | Resources confirmed
Decisions Required | Budget re-baseline approval | 🔴 | Pending sponsor review
Escalations | None | 🟢

## 📌 More Info
Excel Gurukul Online — Additional Resources
More Support | Excel Gurukul Online | Action / Link
Need More Excel Templates? | Visit our website for 500+ free & premium templates | https://excelgurukulonline.com/
Browse by Category | 20 categories — Project Management, HR, Finance & more | https://excelgurukulonline.com/templates.php
Project Management Templates | Gantt Charts, Risk Registers, RACI Matrix & more | https://excelgurukulonline.com/templates.php?cat=project-management
HR & Workforce Templates | Attendance, Payroll, Appraisal & more | https://excelgurukulonline.com/templates.php?cat=hr-workforce
Finance & Budget Templates | Budget Planners, EMI Calculator, Debt Tracker & more | https://excelgurukulonline.com/templates.php?cat=personal-finance
Contact / Special Requirements | Need a customised template? We can help! | info@excelgurukulonline.com
💡 TIP: All templates on Excel Gurukul Online are built from real-world business experience. Free samples are available across all 20 categories. Premium versions available at nominal INR pricing.
© 2026 Excel Gurukul Online ¦ excelgurukulonline.com ¦ info@excelgurukulonline.com